## RTM
Bird Game - Requirements Traceability Matrix ¦ Version 1.0 ¦ Final Closure Update 10 August 2026
Requirement ID | Requirement Summary | Jira Story | Test Scenario(s) | Test Case(s) | Design Coverage | Execution Result | Defect / Blocker | Notes / Open Point
BR-FR-001 | Initial game state | BG-8 | TS-START-001 | TC-START-001 | Covered - Design Complete | Pass after retest | BG-27 (Done) | Initial failure retained in execution history. After BG-27 fix, TC-START-001 passed retest and the first obstacle was visible in the initial state.
BR-FR-002 | Idle before start | BG-9 | TS-START-002 | TC-START-002 | Covered - Design Complete | Pass after blocker removed | BG-27 (Done) | Initially blocked because the obstacle was not visible. After BG-27 fix, TC-START-002 passed retest: bird and obstacle remained stationary before player input.
BR-FR-003 | Supported controls start game | BG-10 | TS-START-003 | TC-START-003, TC-START-004, TC-START-005, TC-START-006, TC-START-007, TC-START-008 | Covered - Design Complete | Pass with observation | BG-28 (Done - Not Reproducible) | Initial TC-START-006 manual failure retained. Subsequent manual retest was inconsistent, while 20 independent controlled Chromium mouse-click start executions passed. BG-28 closed as Not Reproducible with no BG-28-specific code change.
BR-FR-004 | Up Arrow continuous upward movement | BG-11 | TS-MOVE-001 | TC-MOVE-001 | Covered - Design Complete | Pass |  | TC-MOVE-001 passed.
BR-FR-005 | Down Arrow continuous downward movement | BG-11 | TS-MOVE-001 | TC-MOVE-002 | Covered - Design Complete | Pass |  | TC-MOVE-002 passed.
BR-FR-006 | Space single upward jump | BG-12 | TS-MOVE-002 | TC-MOVE-003 | Covered - Design Complete | Pass |  | TC-MOVE-003 passed.
BR-FR-007 | Mouse click single upward jump | BG-12 | TS-MOVE-002 | TC-MOVE-004 | Covered - Design Complete | Pass |  | TC-MOVE-004 passed during active gameplay.
BR-FR-008 | On-screen Up/Down continuous movement | BG-11 | TS-MOVE-003 | TC-MOVE-005, TC-MOVE-006 | Covered - Design Complete | Pass |  | TC-MOVE-005 and TC-MOVE-006 passed.
BR-FR-009 | Gravity when not manually moving | BG-13 | TS-MOVE-004 | TC-MOVE-007 | Covered - Design Complete | Pass |  | TC-MOVE-007 passed.
BR-FR-010 | Obstacle moves right to left | BG-14 | TS-OBS-001 | TC-OBS-001 | Covered - Design Complete | Pass |  | TC-OBS-001 passed.
BR-FR-011 | Obstacle recycles to right | BG-14 | TS-OBS-001 | TC-OBS-002 | Covered - Design Complete | Pass |  | TC-OBS-002 passed.
BR-FR-012 | Opening randomises on reset | BG-15 | TS-OBS-002 | TC-OBS-003 | Covered - Design Complete | Pass |  | TC-OBS-003 passed.
BR-FR-013 | Opening fixed 160px and valid position | BG-15 | TS-OBS-003 | TC-OBS-004, TC-OBS-005 | Covered - Design Complete | Pass |  | TC-OBS-004 and TC-OBS-005 passed.
BR-FR-014 | Starting score 0 | BG-16 | TS-SCORE-001 | TC-SCORE-001 | Covered - Design Complete | Pass |  | TC-SCORE-001 passed.
BR-FR-015 | Award 1 point for successful pass | BG-17 | TS-SCORE-002 | TC-SCORE-003, TC-SCORE-005 | Covered - Design Complete | Pass |  | TC-SCORE-003 and TC-SCORE-005 passed.
BR-FR-016 | Same pass scores only once | BG-17 | TS-SCORE-003 | TC-SCORE-004, TC-SCORE-005 | Covered - Design Complete | Pass |  | TC-SCORE-004 and TC-SCORE-005 passed.
BR-FR-017 | Score visible during gameplay | BG-16 | TS-SCORE-001 | TC-SCORE-002 | Covered - Design Complete | Pass |  | TC-SCORE-002 passed.
BR-FR-018 | Pipe collision Game Over | BG-18 | TS-COLL-001 | TC-COLL-001, TC-COLL-002 | Covered - Design Complete | Pass |  | TC-COLL-001 and TC-COLL-002 passed.
BR-FR-019 | Top/bottom boundary Game Over | BG-18 | TS-COLL-002 | TC-COLL-003, TC-COLL-004 | Covered - Design Complete | Pass |  | TC-COLL-003 and TC-COLL-004 passed.
BR-FR-020 | Safe opening passage no collision | BG-18 | TS-COLL-003 | TC-COLL-005 | Covered - Design Complete | Pass |  | TC-COLL-005 passed.
BR-FR-021 | Game Over state behaviour | BG-19 | TS-GO-001 | TC-GO-001, TC-GO-002, TC-GO-003, TC-GO-004 | Covered - Design Complete | Pass |  | TC-GO-001 to TC-GO-004 passed.
BR-FR-022 | Restart button available | BG-20 | TS-RESTART-001 | TC-RESTART-001 | Covered - Design Complete | Pass |  | TC-RESTART-001 passed.
BR-FR-023 | Restart resets state | BG-21 | TS-RESTART-002 | TC-RESTART-002 | Covered - Design Complete | Pass |  | TC-RESTART-002 passed.
BR-FR-024 | Restart returns to idle | BG-21 | TS-RESTART-002 | TC-RESTART-003 | Covered - Design Complete | Pass |  | TC-RESTART-003 passed.
BR-NFR-001 | Chrome/Edge/Firefox compatibility | BG-22 | TS-COMP-001 | TC-COMP-001, TC-COMP-002, TC-COMP-003 | Covered - Design Complete | Pass |  | Core gameplay flow passed in Chrome, Microsoft Edge and Mozilla Firefox. Exact Edge and Firefox versions were not recorded.
BR-NFR-002 | Smaller-screen usability / controls | BG-23 | TS-RESP-001 | TC-RESP-001 | Covered - Open Point | Pass - representative smaller screen |  | Representative smaller-screen test passed. Minimum supported screen size/resolution remains undefined, so exact boundary coverage remains an open point.