## Defect Log
Bird Game - Defect Log v1.0 ¦ Final Closure Update ¦ 10 August 2026
Defect ID | Summary | Related Test Case | Requirement | Jira Story | Severity | Priority | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Status | Evidence | Retest Result | Notes
BG-27 | First obstacle is not visible in the initial game state | TC-START-001; TC-START-002 (blocked) | BR-FR-001 | BG-8 | Medium | Medium | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html | Bird Game v1 local build is available. Game is opened in Chrome. No gameplay control has been used. | 1. Open source/index.html in Google Chrome. 2. Do not use any controls. 3. Observe the initial game state. 4. Reload with Ctrl + R and observe again. | Initial state displays the bird, first obstacle, score 0 and start instructions. | The bird, score 0 and start instructions are visible, but the first obstacle is not visible. The issue remains after Ctrl + R. | Done | TC-START-001_Initial_State_FAIL_2026-08-10.png; TC-START-001_BG-27_RETEST_PASS_2026-08-10.png; TC-START-002_BG-27_RETEST_PASS_2026-08-10.png | PASS - TC-START-001 and TC-START-002 passed retest | Root cause: initial obstacle was positioned at game.clientWidth, fully outside the visible game area. Fix: initial position changed to game.clientWidth - obstacle.offsetWidth; recycle behaviour unchanged. BG-27 closed after successful retest.
BG-28 | Mouse click does not start gameplay from the initial state | TC-START-006 | BR-FR-003 | BG-10 | Medium | Medium | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html | Bird Game v1 local build is available. Game is in the initial idle state. No keyboard or on-screen control has been used. | 1. Open source/index.html in Google Chrome. 2. Do not press a keyboard key or use on-screen controls. 3. Click once inside the game area. 4. Observe behaviour. 5. Reload with Ctrl + R and repeat. | A single mouse click inside the game area starts gameplay, produces one upward jump and removes the start instruction. | Clicking inside the game area does not start gameplay. The bird does not jump and the start instruction remains visible. The issue is reproducible after reload. | Done | TC-START-006_Mouse_Click_Start_FAIL_2026-08-10.png; BG-28_Controlled_Chromium_Retest_20_Attempts_VALID_2026-08-10.csv | NOT REPRODUCIBLE - controlled Chromium retest 20/20 PASS | No BG-28-specific code change was made. Manual retesting produced inconsistent behaviour, while 20 independent controlled Chromium executions passed. Defect closed as Not Reproducible; original manual failure remains retained for traceability.