## Defect Status
BIRD GAME - FINAL DEFECT STATUS SUMMARY
Project-level position after manual testing and Playwright automation ¦ 11 August 2026
Jira ID | Summary | Origin | Severity | Priority | Final Status | Disposition / Evidence | Residual Risk
BG-27 | First obstacle is not visible in the initial game state | Manual execution | Medium | Medium | Done - Fixed | Initial obstacle-position correction applied. TC-START-001 and TC-START-002 passed retest. | None open from this defect.
BG-28 | Mouse click does not start gameplay from the initial state | Manual execution | Medium | Medium | Done - Not Reproducible | No BG-28-specific code change. Controlled Chromium repeat testing passed 20/20; earlier inconsistent manual observation retained. | Environment/manual inconsistency retained as historical observation.
BG-30 | Game speed varies with browser/display frame rate due to frame-based movement calculations | Playwright automation | Medium | Medium | Open - Known Issue | Baseline uses per-frame movement inside requestAnimationFrame. Automation completion does not mark this fixed. | Gameplay speed may vary across rendering frame rates; retained transparently for portfolio closure.
FINAL PROJECT INTERPRETATION
The manual test cycle closed on 10 August 2026 with BG-27 and BG-28 dispositioned. BG-30 was discovered later during Playwright automation and therefore does not invalidate the historical manual-cycle closure records. The portfolio is complete for presentation with BG-30 explicitly retained as a known open technical issue.
Metric |  | Result
Defects recorded across project |  | 3
Closed defects |  | 2
Open known issues |  | 1
Automation task BG-29 |  | Done