## Execution Log
Bird Game - Manual Test Execution Log ¦ Version 1.0 ¦ Final Closure Update ¦ 10 August 2026
Test Case ID | Requirement(s) | Jira Story | Test Case Title | Actual Result | Status | Environment | Evidence | Defect ID | Execution Notes | Retest Result | Retest Evidence | Final Disposition
TC-START-001 | BR-FR-001 | BG-8 | Verify initial game state | The game opened with the bird visible, score displayed as 0, and the start instruction displayed. However, the first obstacle was not visible in the initial game state. | Fail | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html | TC-START-001_Initial_State_FAIL_2026-08-10.png | BG-27 | Issue reproduced after Ctrl + R. First obstacle remained absent in the initial game state. | PASS - BG-27 retest | TC-START-001_BG-27_RETEST_PASS_2026-08-10.png | Pass after BG-27 fix
TC-START-002 | BR-FR-002 | BG-9 | Verify game remains idle before start | The bird remained stationary for approximately 3 seconds without any player input. However, the obstacle was not visible due to BG-27, so its idle behaviour could not be verified. | Blocked | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html | TC-START-001_Initial_State_FAIL_2026-08-10.png | BG-27 | Blocked by BG-27 because the first obstacle is absent from the initial game state. Bird idle behaviour was verified successfully, but obstacle idle behaviour could not be tested. | PASS - blocker removed and retested | TC-START-002_BG-27_RETEST_PASS_2026-08-10.png | Pass after BG-27 blocker removed
TC-START-003 | BR-FR-003 | BG-10 | Start game with Up Arrow | Pressing and briefly holding the Up Arrow started gameplay. The bird moved upward while the Up Arrow was held, and the start instruction disappeared. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-START-004 | BR-FR-003 | BG-10 | Start game with Down Arrow | Pressing and briefly holding the Down Arrow started gameplay. The bird moved downward while the Down Arrow was held, and the start instruction disappeared. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-START-005 | BR-FR-003 | BG-10 | Start game with Space | Pressing the Space bar once started gameplay. The bird performed an upward jump and the start instruction disappeared. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-START-006 | BR-FR-003 | BG-10 | Start game with mouse click | Clicking once inside the game area did not start gameplay. The bird did not perform an upward jump and the start instruction remained visible. | Fail | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html | TC-START-006_Mouse_Click_Start_FAIL_2026-08-10.png | BG-28 | Issue reproduced after Ctrl + R. Clicking inside the game area did not start gameplay on the repeated attempt. | Controlled Chromium: 20/20 PASS; manual retest inconsistent | BG-28_Controlled_Chromium_Retest_20_Attempts_VALID_2026-08-10.csv | Closed - Not Reproducible (BG-28); observation retained
TC-START-007 | BR-FR-003 | BG-10 | Start game with on-screen Up button | Using the on-screen Up control started gameplay. The bird moved upward while the control was held, and the start instruction disappeared. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-START-008 | BR-FR-003 | BG-10 | Start game with on-screen Down button | Using the on-screen Down control started gameplay. The bird moved downward while the control was held, and the start instruction disappeared. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-MOVE-001 | BR-FR-004 | BG-11 | Verify Up Arrow continuous movement and release | The bird moved upward continuously while the Up Arrow was held and the expected release behaviour was observed. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-MOVE-002 | BR-FR-005 | BG-11 | Verify Down Arrow continuous movement and release | The bird moved downward continuously while the Down Arrow was held and the expected release behaviour was observed. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-MOVE-003 | BR-FR-006 | BG-12 | Verify Space gives a single upward jump | A single press of the Space bar produced one upward jump as expected. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-MOVE-004 | BR-FR-007 | BG-12 | Verify mouse click gives a single upward jump | During active gameplay, a mouse click produced one upward jump as expected. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-MOVE-005 | BR-FR-008 | BG-11 | Verify on-screen Up continuous movement | The bird moved upward continuously while the on-screen Up control was held. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-MOVE-006 | BR-FR-008 | BG-11 | Verify on-screen Down continuous movement | The bird moved downward continuously while the on-screen Down control was held. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-MOVE-007 | BR-FR-009 | BG-13 | Verify gravity after manual input stops | After manual input stopped, gravity moved the bird downward as expected. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-OBS-001 | BR-FR-010 | BG-14 | Verify obstacle moves right to left | The obstacle moved continuously from right to left during gameplay. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-OBS-002 | BR-FR-011 | BG-14 | Verify obstacle recycles after leaving left edge | After leaving the left edge, the obstacle reappeared from the right and continued through the play area. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-OBS-003 | BR-FR-012 | BG-15 | Verify opening position randomises on reset | The obstacle opening appeared at different vertical positions after successive resets. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-OBS-004 | BR-FR-013 | BG-15 | Verify obstacle opening height is 160px | The obstacle opening matched the specified 160 px height. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-OBS-005 | BR-FR-013 | BG-15 | Verify opening stays fully inside playable area | The obstacle opening remained fully within the playable area. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-SCORE-001 | BR-FR-014 | BG-16 | Verify starting score is 0 | The score displayed 0 at the start of the game. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-SCORE-002 | BR-FR-017 | BG-16 | Verify score remains visible during gameplay | The score remained visible throughout gameplay. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-SCORE-003 | BR-FR-015 | BG-17 | Verify score increments after successful pass | The score increased by one after a successful obstacle pass. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-SCORE-004 | BR-FR-016 | BG-17 | Verify no duplicate scoring for same pass | A successful obstacle pass was counted once only; no duplicate score was added for the same pass. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-SCORE-005 | BR-FR-015; BR-FR-016 | BG-17 | Verify later recycled pass can score again | A later successful pass after obstacle recycling increased the score again without duplicating the earlier pass. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-COLL-001 | BR-FR-018 | BG-18 | Verify upper pipe collision triggers Game Over | Contact with the upper pipe triggered Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-COLL-002 | BR-FR-018 | BG-18 | Verify lower pipe collision triggers Game Over | Contact with the lower pipe triggered Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-COLL-003 | BR-FR-019 | BG-18 | Verify top boundary triggers Game Over | Contact with the top boundary triggered Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-COLL-004 | BR-FR-019 | BG-18 | Verify bottom boundary triggers Game Over | Contact with the bottom boundary triggered Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-COLL-005 | BR-FR-020 | BG-18 | Verify safe gap passage does not trigger Game Over | Passing safely through the obstacle gap did not trigger Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-GO-001 | BR-FR-021 | BG-19 | Verify gameplay stops after Game Over | Gameplay stopped when Game Over was triggered. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-GO-002 | BR-FR-021 | BG-19 | Verify no scoring after Game Over | The score did not increase after Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-GO-003 | BR-FR-021 | BG-19 | Verify final score is shown | The final score remained visible after Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-GO-004 | BR-FR-021 | BG-19 | Verify movement controls are disabled after Game Over | Movement controls no longer moved the bird after Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-RESTART-001 | BR-FR-022 | BG-20 | Verify Restart button is available after Game Over | The Restart button was available after Game Over. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-RESTART-002 | BR-FR-023 | BG-21 | Verify Restart resets score/bird/obstacle/instructions | Restart reset the score, bird, obstacle and start instructions to the expected initial state. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-RESTART-003 | BR-FR-024 | BG-21 | Verify Restart returns to idle without auto-start | After Restart, the game returned to the idle state and did not start automatically. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-COMP-001 | BR-NFR-001 | BG-22 | Verify core gameplay flow in Google Chrome | The core gameplay flow completed successfully in Google Chrome. | Pass | Windows desktop ¦ Google Chrome 151.0.7922.109 (64-bit) ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-COMP-002 | BR-NFR-001 | BG-22 | Verify core gameplay flow in Microsoft Edge | The core gameplay flow completed successfully in Microsoft Edge. | Pass | Windows desktop ¦ Microsoft Edge ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-COMP-003 | BR-NFR-001 | BG-22 | Verify core gameplay flow in Mozilla Firefox | The core gameplay flow completed successfully in Mozilla Firefox. | Pass | Windows desktop ¦ Mozilla Firefox ¦ Bird Game v1 local build ¦ source/index.html |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged
TC-RESP-001 | BR-NFR-002 | BG-23 | Verify layout and controls on representative smaller screen | The layout remained usable and the on-screen controls remained available on the representative smaller-screen configuration. | Pass | Windows desktop ¦ Representative smaller-screen configuration ¦ Bird Game v1 local build |  |  | Expected behaviour observed. No defect identified. | Not required |  | Pass - unchanged

## Summary
Bird Game - Test Execution Summary ¦ Final Closure
Project | Bird Game QA Portfolio |  | Initial Execution | Result |  | Final Closure | Result
Test cycle | Manual Test Cycle v1.0 |  | Total planned | 41 |  | Confirmed Pass | 40
Execution date | 10 August 2026 |  | Pass | 38 |  | Closed - Not Reproducible | 1
Closure date | 10 August 2026 |  | Fail | 2 |  | Open Fail | 0
Build / source | Bird Game v1 local build ¦ source/index.html |  | Blocked | 1 |  | Blocked | 0
|  |  | Not Run | 0 |  | Open defects | 0
|  |  | Execution completion | 100% |  | Defects closed | 2
|  |  | Pass rate | 92.68% |  | Disposition completion | 100%
Final Defect Register
Defect ID | Summary | Final Status | Resolution | Related Test(s) | Retest Outcome | Code Change | Residual Note
BG-27 | First obstacle is not visible in the initial game state | Done | Fixed | TC-START-001; TC-START-002 | Both tests PASS on retest | Initial obstacle position corrected | No open blocker.
BG-28 | Mouse click does not start gameplay from the initial state | Done | Not Reproducible | TC-START-006 | 20/20 controlled Chromium PASS; manual inconsistency retained | No BG-28-specific code change | Environment-specific/manual inconsistency retained as observation.
Closure outcome: the initial execution history remains 38 Pass, 2 Fail and 1 Blocked. BG-27 was fixed and both affected tests passed retest. BG-28 was closed as Not Reproducible after 20/20 controlled Chromium passes, while the inconsistent manual observation was retained. At closure there are 40 confirmed Pass dispositions, 1 closed Not Reproducible observation, 0 open Fail, 0 Blocked and 0 open defects.
Residual traceability note: minimum supported smaller-screen dimensions remain undefined; exact Edge and Firefox versions were not recorded; BG-28's environment-specific/manual inconsistency remains documented. No full regression cycle was executed after the BG-27 fix; closure is based on targeted retest and defect disposition.